# Chapter 2
Executing Strategy: Project Management

## Multiple Choice

1. Which of the following is NOT an example of a project?

a) Constructing highways, bridges, tunnels and dams

b) Managing research and development (R&D) activities such as the development of the atomic bomb

c) Building a long tunnel

d) Running political or advertising campaigns, war or fire-fighting operations

e) Building MP3 players for massive distribution

Answer: E

Difficulty: Easy

Reference: Defining a Project

2. Among the reasons for the growth in project operations we find:

a) People have more leisure time to follow and participate in projects

b) More sophisticated technology has increased public awareness of project operations

c) More customization for suppliers makes it important to meet their needs

d) Both A and B

Answer: D

Difficulty: Medium

Reference: Defining a Project

3. Which of the following project categories typically seeks the development of a new generation of outputs?

a) Derivative projects

b) Breakthrough projects

c) Platform projects

d) R&D projects

e) Construction Projects

Answer: B

Difficulty: Medium

Reference: Planning the Project

4. Which of the following project categories might lead to the other project categories?

a) Derivative projects

b) Breakthrough projects

c) Platform projects

d) R&D projects

e) None of the above

Answer: D

Difficulty: Medium

Reference: Planning the Project

5. Project charters should contain some level of information regarding which of the following elements:

a) Business case, goals, or scope

b) Overview, general approach, schedules or milestones

c) Work breakdown structure and path dependencies

d) Both A and B

e) None of the above

Answer: D

Difficulty: Medium

Reference: Planning the Project

6. Which of the following terms provides the basis for the project schedule, often formatted as a project Gantt chart?

a) Critical path

b) Slack

c) Float

d) Earned value

e) Work breakdown structure

Answer: E

Difficulty: Medium

Reference: Planning the Project

7. The set of all project activities graphically interrelated through precedence relationships is known as a/an:

a) Activity

b) Event

c) Network

d) d) Path

e) Gantt chart

Answer: C

Difficulty: Medium

Reference: Scheduling the Project

8. Any path that if delayed will delay the completion of the entire project is known as a:

a) Significant path

b) Critical path

c) Central path

d) Network path

e) Troublesome path

Answer: B

Difficulty: Easy

Reference: Scheduling the Project

9. All of the following are important outputs of project scheduling, except:

a) Identification of slack times for all activities and paths

b) Earliest and latest time each activity can be completed

c) Networks and paths

d) Identification of critical activities

Answer: C

Difficulty: Easy

Reference: Scheduling the Project

10. The amount of flexibility the project manager has in terms of starting and completing an activity is referred to as its:

a) Slack

b) Float

c) Flex

d) Give

e) Both A and B

Answer: E

Difficulty: Easy

Reference: Scheduling the Project

11. Duration of critical path – path duration = __________?

a) Latest finish time

b) Critical time

c) Path slack

d) Latest start time

e) Project slack

Answer: C

Difficulty: Medium

Reference: Scheduling the Project

12. The amount of time a project manager estimates it will take to complete the activity under ideal conditions is known as:

a) Pessimistic time

b) Optimistic time

c) Likeliest time

d) Utopian time

e) Slack time

Answer: B

Difficulty: Easy

Reference: Scheduling the Project

13. Which of the following statement(s) concerning probabilities of completion is/are incorrect?

a) Using the variance of each activity, we can compute the likelihood of completing the project in a given time period.

b) The probability of completing a path is found by calculating the standard normal deviate of the desired completion time less the expected completion time.

c) The distribution of a path’s completion time will be approximately normally distributed if the path has a large number of activities on it.

d) The individual activity completion times must be normally distributed

e) All of the above are incorrect

Answer: D

Difficulty: Hard

Reference: Scheduling the Project

14. When workers receive approval for a task based on inflated time estimate, they may perceive that they now have plenty of time to complete the task and therefore delay starting the task. What has this concept been called?

a) Senioritis

b) Inflation syndrome

c) Time-shift

d) Goldratt delay

e) Student syndrome

Answer: E

Difficulty: Easy

Reference: Scheduling the Project

15. According to Goldratt, to complete a project on time, the highest priority should be given to the:

a) Critical buffer

b) Feeding chain

c) Project buffer

d) Critical chain

e) Slack activities

Answer: D

Difficulty: Hard

Reference: Scheduling the Project

True/False

16. An optimal procedure for organizations to accept projects is to specify a return on investment (ROI) and fund only projects that meet this criterion.

Answer: False

Difficulty: Easy

Reference: Planning the Project

17. The project life cycle typically has a stretched-s or an exponential form.

Answer: True

Difficulty: Easy

Reference: Planning the Project

18. Projects should be evaluated against standards and by methods established at their completion, including procedures for monitoring, collecting, storing, and evaluating the history of the project.

Answer: True

Difficulty: Hard

Reference: Planning the Project

19. An event is a series of connected activities from the start to the finish of the project.

Answer: False

Difficulty: Easy

Reference: Scheduling the Project

20. The amount of flexibility the project manager has in terms of starting and completing an activity is referred to as its slack.

Answer: True

Difficulty: Easy

Reference: Scheduling the Project

21. The optimistic time is the amount of time the project will take under the worst-case scenario.

Answer: False

Difficulty: Easy

Reference: Scheduling the Project

22. Using CPM, when activity times are not known with certainty, we still can determine how long it will actually take to complete the project.

Answer: False

Difficulty: Easy

Reference: Scheduling the Project

23. Three phenomena that tend to bias the expected completion time of projects are inflated time estimates, activity time variability with path interdependencies, and resource dependence.

Answer: True

Difficulty: Medium

Reference: Scheduling the Project

24. The amount of safety time needed to protect a particular path in a project is less than the sum of the safety times required to protect the individual activities making up the path.

Answer: True

Difficulty: Easy

Reference: Scheduling the Project

25. The objective of feeding buffers is to ensure that non-critical chains are completed so that they do not delay tasks on the critical chain.

Answer: True

Difficulty: Medium

Reference: Scheduling the Project

26. Favorable variances do not require corrective action or further investigation; only unfavorable variances in performance.

Answer: True

Difficulty: Medium

Reference: Controlling the Project: Earned Value

Fill in the Blank

27. Both PERT and CPM are based on variations of the __________ chart?

Answer: Gantt

Difficulty: Hard

Reference: Planning the Process

28. The amount of _____ _____ needed to protect a particular path in a project is less than the sum of the _____ _____ required to protect the individual activities making up the path.

Answer: safety time, safety times

Difficulty: Medium

Reference: Scheduling the Project

29. When a project cost, schedule, or time variance is significant, the project manager must identify (or at least try to do so) an __________ cause for the variance so that the proper remedy can be used to keep it from recurring.

Answer: assignable

Difficulty: Medium

Reference: Controlling the Project: Earned Value

Short Answer

30. Give an example of Inflated Activity Time Estimates.

Answer: Answers will vary. One possible answer is as follows. An employee to a retail store might purposely inflate the time it takes him to recover the store's inventory organization to his managers to buy extra time to complete his job. He will also not report when his actual completion time for fear of management shorting the time span. This would affect the worker to work more quickly and harder to meet completion time.

Difficulty: Easy

Reference: Inflated Activity Time Estimates

31. Give an example of Activity Time Variability with Path Interdependencies.

Answer: Answers will vary. One possible answer is as follows. A gun smith shop, which makes guns upon request, will only start production when a gun is ordered. Assuming all parts is interchangeable. Thus when a gun is ordered then every worker at the shop goes in to action. The time it takes the barrel maker is around three weeks. It takes the stock and handle maker around a month and a half to complete the stock and handles. It takes the bolt maker three months to complete the bolt. Therefore, when the gun shop is giving a customer an estimate on the length of time it takes to complete a gun the answer given will be three months because it takes the bolt maker the longest time out of the production.

Difficulty: Easy

Reference: Activity Time Variability with Path Interdependencies

32. Give an example of Resource Dependence.

Answer: Answers will vary. One possible answer is as follows. A high-end sword shop makes custom swords for well-paying customers. When a sword is ordered the shop goes into action. The sword blade and tang must be forged first because with each hammer stroke the blacksmith is changing the dimensions of the sword meaning two of the same swords are going to be slightly different. When forging is done then the handle, cross-guard, and pommel are fitted custom to that particular sword. Then the scabbard is made for the sword which depended on the shape of the cross-guard and the dimensions of the blade for a perfect fit. The estimated time to completion is the sum of all the activities, which is approximately five months.

Difficulty: Easy

Reference: Resource Dependence

33. What three outcomes must a project manager determine when scheduling a project with uncertain activity times and the significance of each?

Answer: The project manage must develop three estimates, optimistic time, pessimistic time, and most likely time. The optimistic time is the expected time to complete under ideal conditions and would only take less time than this one percent of the time. The pessimist time is the time the project would take under the worst-case scenario; again only a one percent chance it would take longer than this time. The most likely time is the project manager’s best estimate to how long the project will actually take.

Difficulty: Easy

Reference: Project Scheduling with Uncertain Activity Times

34. Briefly describe the importance of a Project charter.

Answer: A project charter describes the purpose of the project as well objectives the project is expected to meet and what determines the project a success. The charter also contains a detailed description of requirements, and resource or budget restrictions that may apply. A project charter thoroughly lists all parties that will be involved directly and indirectly with project team processes. The charter also outlines major scheduling dates and milestones, as well as a contingency plan if problems arise. Lastly the charter contains some form of predetermined evaluation method against established standards.

Difficulty: Easy

Reference: Project Plans

35. How does benchmarking improve operations? And give a relevant example.

Answer: Benchmarking is evaluating your operations to another companies/persons operations to see where it is they are potentially better at, and where you can implement their actions to improve your own. Benchmarking helps one get better plans to correct their problems/issues, helps save money by looking at another company to improve, and lowers time needed to come up with a new idea to a problem when perhaps another company has faced that issue too, and came up with a solution. An example would be the VHA story found on page 35, how they benchmarked other healthcare providers to improve their claim processing abilities.

Difficulty: Easy

Reference: Introduction

36. How are projects not like other typical or routine processes?

Answer: A project is more unique in nature than a typical or routine process. There is often very little “sets of rules/procedures” to follow to correctly navigate to the correct answer to unique projects. A typical routine or process such as building a Chevrolet Malibu is fairly straightforward with very little uniqueness, and has clear-cut guidelines for making it. Whereas something like a wedding is a project that is unique in nature because no weddings are exactly alike, and each user has different desires and needs to be met. Projects take on unique aspects which makes them different from a routine process.

Difficulty: Easy

Reference: Defining a Project

37. Why is a project portfolio a better approach to a project than the ROI approach?

Answer: Because a project portfolio is more diversified and looks at more aspects than just the projects rate of return (ROI). Projects that use a portfolio are more successful, cover a broader range of concerns, and are completed in a more timely manner and come in on budget. Projects too concerned with ROI end up with more incomplete projects that need to be either completed after the due date, or become an ongoing problem.

Difficulty: Moderate

Reference: The Project Portfolio

38. What is the product life cycle (PLC)?

Answer: The product life cycle is the different phases of a products life. The product life cycle includes the initiation, implementation, and termination. These stages vary in time and length according to what the project is, for instance software has a short life cycle because technology is changing basically daily, where as a particular model of a car would have a longer life cycle because car models are typically produced for several years before a new updated model of that car is introduced. Project initiation is usually a slow process because that is when everything is getting organized. The implementation is where a lot of the product progress in the market happens, and termination is where everything slows down.

Difficulty: Easy

Reference: The Project Life Cycle

39. Why is being able to predict activity times crucial in order to meet the demands of your customer?

Answer: Timing is a very important factor when dealing with project management. If a customer comes to you with a project that needs to be done in six months, necessary actions and planning are done in order to make sure you make that deadline. As a project manager you need to know when you have a critical path, critical activity or slack in regards to the previous two paths. If you do not know if you have any of the three things mentioned above, it is very difficult to plan when you will have the project completed.

Difficulty: Moderate

Reference: Calculating Activity Durations

40. Why might it be useful to simulate project completion times?

Answer: Simulating project times using a program like Crystal Ball, helps you set deadlines and have the ability to give the customer the most accurate time frame that can be made. By making a projected deadline, the project manager is able to allocate workers to different tasks on who would fit best for the length of time given. Simulating completion times might also prevent future conflicts from arising such as resource overlap. If the project manager is able to predict when certain tasks will be completed, he will be able to schedule when each resource will be used and where they will need to be.

Difficulty: Moderate

Reference: Simulating Project Completion Times

41. Compare and contrast PERT and CPM.

Answer: The CPM method provides predictable or times for each activity whereas the PERT method has random activity time. PERT activities are shown through the arrow lines between the nodes and CPM are represented as the nodes. PERT gives multiple estimates of times for each activity that allows for variation of activity times.

Difficulty: Easy

Reference: Project Completion and Critical Paths

42. Provide an example of how a project manager can use slack time.

Answer: Answers will vary. One possible answer follows. A project manager can see how much slack the entire project has and compare it to the critical path to get the slack time. The project manager can evaluate this time and find out how to decrease the activity time and where they should invest money to generate a smaller slack time. If the project manager wants to finish a project in 10 days as opposed to 15 days they can look at the activities that has slack and figure out if they can reduce the activity time by five days in a cost effective way.

Difficulty: Moderate

Reference: Slack Time

Essay

43. Explain the importance of slack time and how it can impact the critical path.

Answer: Slack time is the amount of time a project activity may be delayed until where further delay would delay the entire project. Slack time allows a project manager to use resources between activities to help expedite the project. For example projects with slack time can have resources shifted to an activity along the critical path to help facilitate completion, which could result in the project finishing early.

Difficulty: Moderate

Reference: Slack time

44. Describe the four qualities are sought after in a project manager.

Answer: Project managers must be credible in both a technical and administrative capacity to handle the range of important stakeholders. PMs must also be sensitive to the politics and personalities they will be involved with. Projects often have inner conflict as well as conflict with higher administration and outsiders and must detect these conflicts and defuse them before it turns into a crisis. A PM must also have strong leadership skills and competencies that correspond with the appropriate project. Lastly PMs must able to handle stress. Projects are often formed because the organization isn’t able to handle the special task with normal operations. Projects typically have tight schedules and difficult goals that will increase stress level.

Difficulty: Moderate

Reference: Organizing the Project Team

45. Describe the two types of project organizational structure were discussed and the advantages of both.

Answer: The first organizational structure described was functionally structured. In a functionally structures organization the organization is broken up into specific departments and project teams are housed and report to the division that has a major interest in the project. If a broad project is chosen than members from each department are selected to from the project team and then report to a division head or vice president. The primary advantage of functionally organized is the depth of knowledge one particular department would have regarding their own project. The second structure is projectized organizations. In a projectized structure the teams are broken into particular contracts the firm is working on, while the administrative support groups, like HR and finance, are staff units that report higher up in the organization but provide support to all the different teams. If there are particularly large and long running contracts they may have their own dedicated staff. An advantage of a projectized organization is the entire team is dedicated to a common goal that reports to one project manager rather than a chain of supervisors.

Difficulty: Moderate

Reference: Projects in the Organizational Structure

46. Many projects require different emphases during their life cycle. For example, technical performance may be crucial at the beginning, cost overruns in the middle, and on-time completion at the end. Given the project of running a political campaign, what would be there top three emphases starting from the beginning to end?

Answer: Answers will vary. One possible answer is as follows. There is a lot of work that has to come into play when running a political campaign. However, the top three emphases on doing this project would be obtaining the funds to run a successful campaign at the beginning. In the middle of the project is when the technology comes into play- creating ads and commercials, creating websites, etc. Lastly, to run a successful political campaign, the candidate, after having the funds and ads, must schedule meetings with the press and any political debates necessary.

Difficulty: Moderate

Reference: Defining a Project

47. Give an example of a derivative project and explain why your reasoning.

Answer: Answers will vary. One possible answer is as follows. A derivative project is defined as a project that seeks to make incremental improvements in the output and/or process. They seek to reduce the output’s cost or make minor product line extensions. An example of this would be Apple’s innovation in annually changing the shape and design of their iPhones. By slimming down the size of their iPhones, they are reducing the output’s cost. Sometimes, when Apple adds a feature to the iPhone, this also falls into the category of a derivative project because they are making minor production line extensions.

Difficulty: Moderate

Reference: The Project Portfolio

48. Give an example of a project with the exponential life cycle and describe why this is a good example.

Answer: A good example of the exponential life cycle would be anything that requires constant work to result in one final piece. One example of this could be a student at Kennesaw State University working towards their Bachelor’s degree. A lot of work is put in to getting this degree- taking classes, making good grades, staying up on school payments, and results in an end result, the degree. Another example of this could be an advertisement. The company must initially contact an ad agency, and from there the ad agency gathers information such as the target market, information about the product and competition, etc. Eventually, the ad agency will come back to the company with one completed piece of an ad. These two examples are great when it comes to defining the exponential life cycle of a project.

Difficulty: Moderate

Reference: The Project Life Cycle